## Week 1
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-02-06 | 11:00 | 11:30 | Client Meeting #1 | 0.5 | Meeting went well and follow up with more items - refer to issues
2019-02-06 | 12:30 | 15:00 | Class | 2.5 | Outline of needs this trimester - will have lectures on topics
2019-02-07 | 18:30 | 22:00 | Learning outcomes spreadsheet | 3.5 | Filled and gave a good indication as to how to plan the project and what to achieve in terms of goals and marketing
|  |  | NDA Form |  | Good insight into NDA which I have never thought of
2019-02-08 | 11:00 | 15:30 | Project Management | 4.5 | Handling issues etc
|  |  | Content Management |  | Organising Github
|  |  | Writing Wikis |  | Github, Wordpress, License - used the wrong wordpress installation. Have to re-install and re-write wikis
Can't run admin IWP - will install to laptop and test
Need to test github clone
Maybe use laptop for all the coding for this project
2019-02-08 | 19:00 | 21:00 | Marketing plan research | 2 | Begun research on how to write marketing plan
|  |  | Surverys written |  | Conducting 2 surverys - one for client, one for demographic
|  |  | Tested Github clone |  | Clone is working, decided to use only my laptop for project due to database
2019-02-10 | 19:00 | 21:00 | Research competitors | 2 | Aim was to work on project marketing plan but tired. Instead researched some local bands that can be seen as competitors
|  |  | Research website designs |  | Looked at some website designs as inspiration
2019-02-11 | 15:30 | 22:00 |  | 6.5 | Finished research for marketing analysis Wrote marketing analysis Conducted interview with Nick Bragg
2019-02-13 | 15:00 | 20:00 | Finish marketing plan | 5 | Editing final elements, added references
Typed Reflective blog
|  |  | Updated Wiki |  | Wordpress details and license
|  |  | Uploaded docs to GitHub |  | Client docs
|  |  | Wrote Client Brief doc |  | All printed and ready for meeting with client tomorrow
Total Hours |  |  |  | 26.5

## Week 2
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-02-13 | 11:30 | 12:00 | Client Meeting #2 | 0.5 | Presented Client Brief doc and Marketing Analysis
2019-02-13 | 12:00 | 15:00 | Class | 3 | Refer to lecture notes Closed some issues with Gantt Chart and License
2019-02-13 | 16:00 | 17:00 | Reviewed documents | 1 | Looked over documents from day Drafted email to client for follow up
2019-02-14 | 15:00 | 18:00 | Project management | 3 | Researching style guide elements
|  |  | Emailed client |  | Follow up email with client
|  |  | Research |  | Researching moodboard
2019-02-15 | 18:00 | 21:00 | Research inspiring websites | 3 | One page website seems to be the way to go with the merch page directing to a difference section of the site. Maybe a few other things leading off as well
Began style guide
2019-02-16 | 18:00 | 21:00 | Style Guide | 3 | Began the template for my style guide Looked at Adobe stock for template ideas Continuted my research on styles
2019-02-17 | 16:00 | 22:00 | Style Guide | 6 | Began collating my research images and information Created some assets for the style guide Completed 90% of the guide
2019-02-18 | 17:00 | 22:00 | Style Guide | 5 | Finished the guide and printed off Realised I had set the project up wrong in InDesign so I had to reformat some things. I hadn't set up for print so CMYK was not set and it was in RGB. Also had the pages at a screen resolution instead of a4
2019-02-19 | 18:00 | 11:30 | Style Guide | 5.5 | Printed and collated the style guide
Project management
|  |  | Project Overview |  | Wrote an outline for client about project goals and how it will be achieved. Just an overview for the record.
|  |  | Structured metadata |  | Revisited my research from last trimester. Found some new articles which were interesting.
Total Hours |  |  |  | 30

## Week 3
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-02-20 | 16:00 | 16:30 | Client Meeting #2 | 0.5 | Presented Style Guide and Project Overview Discussed photography for band Discussed style and layout ideas
2019-02-20 | 12:00 | 15:00 | Class | 3 | Refer to lecture notes Closed some issues with Gantt Chart
2019-02-21 | 14:00 | 16:00 | Research WordPress | 2 | Looked at some options with WordPress and what I can do. Still experimenting. Wanted to spend more time on it today but I was tired.
2019-02-22 | 20:00 | 21:00 | Drafted wireframes | 1
2019-02-23 | 15:00 | 17:00 | Research WordPress | 2 | Found how to do front end hosting with WordPress which would be an easier workflow
2019-02-24 |  |  |  | 2 | Food poisoning for the remainder of the week resulting in work time lost. I spend a little time trying to set up my host provider so I can use WordPress on the front end, howevver none of my other work was completed.
Total Hours |  |  |  | 10.5

## Week 4
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-02-27 |  |  |  |  | Missed class
2019-03-02 | 15:00 | 19:30 | Project management with Github | 6 | Combing tasks that need updating and reassignment
|  |  | Emailed Greg |  | Requirements
|  |  | Emailed Walter |  | Overview
|  |  | Catch up research readings |  | Structured metadata research from week 2
|  |  | Setup Wireframe |  | Began drafting HiFi wireframe
2019-03-03 | 17:00 | 23:00 | Wireframe and research | 6 | Starting to realised I need to research WordPress a lot more but I think it will need to be fast tracked. A lot of my designing and learning will happen during the development phase of this project. With mockups I might also fast track that with an emphasis on design changes
Total Hours |  |  |  | 12

## Week 5
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-03-06 | 11:00 | 12:00 | Met with Rob | 1 | Discussed hosting, timeline for project, WordPress plugins
|  |  | Met with Heli |  | Discussed photos, mockups, hosting, budget
2019-03-07 | 13:00 | 17:00 | Updated GitHub | 4 | Not many new issues, just researching wordpress still
|  |  | Client Communication |  | emailed heli
|  |  | Emailed Paul Morris |  | Trying to find a day to look at geat at SAE for photography
|  |  | Wordpress research |  | had issues with my hosting provider, I'm temporarily using my own domain to test my platform out unpublished
2019-03-08 | 13:00 | 19:00 | Wordpress research | 6 | Found some plugins that look good. Sadly the gear html5 plugin looks like it won't work. Would like to try anyway with iFrame.
|  |  | Spoke to Gregory Gautier |  | Chatted about design
|  |  | Mockup Design |  | Working on Mockup
2019-03-09 | 13:00 | 20:00 | Mockup Design | 7 | need client to give me content - request this after mockup completion
need photos of band to be bright and colourful
Background needs to be less noisy to make that font work (poiret One)
use bold on fonts - doesn't work in mockup app
changed to two different backgrounds: grunge texture and paint splatters. With too much happening in the background the text is too difficult to read
Finished basic mockup to focus on style and layout. True design will show in development phase
|  |  | Updated github |  | Closed issues, updated research
|  |  | Emailed client |  | Send draft mockup to client
2019-03-10 | 19:00 | 21:00 | Plugin research | 2 | Found updraft plus for backup - works with download or host, can schedule backups etc
|  |  | Github project management |  | Updating taskings, filling out reflective blog
|  |  | Communication Management |  | Collecting emails for documentation
Total Hours |  |  |  | 20