## Week 1
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-02-06 | 11:00 | 11:30 | Client Meeting #1 | 0.5 | Meeting went well and follow up with more items - refer to issues
2019-02-06 | 12:30 | 15:00 | Class | 2.5 | Outline of needs this trimester - will have lectures on topics
2019-02-07 | 18:30 | 22:00 | Learning outcomes spreadsheet | 3.5 | Filled and gave a good indication as to how to plan the project and what to achieve in terms of goals and marketing
|  |  | NDA Form |  | Good insight into NDA which I have never thought of
2019-02-08 | 11:00 | 15:30 | Project Management | 4.5 | Handling issues etc
|  |  | Content Management |  | Organising Github
|  |  | Writing Wikis |  | Github, Wordpress, License - used the wrong wordpress installation. Have to re-install and re-write wikis
Can't run admin IWP - will install to laptop and test
Need to test github clone
Maybe use laptop for all the coding for this project
2019-02-08 | 19:00 | 21:00 | Marketing plan research | 2 | Begun research on how to write marketing plan
|  |  | Surverys written |  | Conducting 2 surverys - one for client, one for demographic
|  |  | Tested Github clone |  | Clone is working, decided to use only my laptop for project due to database
2019-02-10 | 19:00 | 21:00 | Research competitors | 2 | Aim was to work on project marketing plan but tired. Instead researched some local bands that can be seen as competitors
|  |  | Research website designs |  | Looked at some website designs as inspiration
2019-02-11 | 15:30 | 22:00 |  | 6.5 | Finished research for marketing analysis Wrote marketing analysis Conducted interview with Nick Bragg
2019-02-13 | 15:00 | 20:00 | Finish marketing plan | 5 | Editing final elements, added references
Typed Reflective blog
|  |  | Updated Wiki |  | Wordpress details and license
|  |  | Uploaded docs to GitHub |  | Client docs
|  |  | Wrote Client Brief doc |  | All printed and ready for meeting with client tomorrow
Total Hours |  |  |  | 26.5

## Week 2
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-02-13 | 11:30 | 12:00 | Client Meeting #2 | 0.5 | Presented Client Brief doc and Marketing Analysis
2019-02-13 | 12:00 | 15:00 | Class | 3 | Refer to lecture notes Closed some issues with Gantt Chart and License
2019-02-13 | 16:00 | 17:00 | Reviewed documents | 1 | Looked over documents from day Drafted email to client for follow up
2019-02-14 | 15:00 | 18:00 | Project management | 3 | Researching style guide elements
|  |  | Emailed client |  | Follow up email with client
|  |  | Research |  | Researching moodboard
2019-02-15 | 18:00 | 21:00 | Research inspiring websites | 3 | One page website seems to be the way to go with the merch page directing to a difference section of the site. Maybe a few other things leading off as well
Began style guide
2019-02-16 | 18:00 | 21:00 | Style Guide | 3 | Began the template for my style guide Looked at Adobe stock for template ideas Continuted my research on styles
2019-02-17 | 16:00 | 22:00 | Style Guide | 6 | Began collating my research images and information Created some assets for the style guide Completed 90% of the guide
2019-02-18 | 17:00 | 22:00 | Style Guide | 5 | Finished the guide and printed off Realised I had set the project up wrong in InDesign so I had to reformat some things. I hadn't set up for print so CMYK was not set and it was in RGB. Also had the pages at a screen resolution instead of a4
2019-02-19 | 18:00 | 11:30 | Style Guide | 5.5 | Printed and collated the style guide
Project management
|  |  | Project Overview |  | Wrote an outline for client about project goals and how it will be achieved. Just an overview for the record.
|  |  | Structured metadata |  | Revisited my research from last trimester. Found some new articles which were interesting.
Total Hours |  |  |  | 30

## Week 3
Date | Logged In | Logged Out | Tasks Completed | Hours | Blog Notes
2019-02-13 | 16:00 | 16:30 | Client Meeting #2 | 0.5 | Presented Style Guide and Project Overview Discussed photography for band Discussed style and layout ideas
2019-02-13 | 12:00 | 15:00 | Class | 3 | Refer to lecture notes Closed some issues with Gantt Chart
2019-02-14 | 14:00 | 16:00 | Research WordPress | 2 | Looked at some options with WordPress and what I can do. Still experimenting. Wanted to spend more time on it today but I was tired.
2019-02-15 | 20:00 | 21:00 | Drafted wireframes | 1
Total Hours |  |  |  | 6.5